## Internship Tracker
Yenepoya Internship Tracker - 2026
Task ID | Task Description | Project Title | Student Name | Campus ID | Specialization | Semester | Project Timeline | Start Date | End Date | Status | Feedback and Comments
SC-01 | Project Planning & Requirement Gathering (Logistics, Cargo Security) | Design and Development of Identity Security Framework for Supply Chain | Mohammed Nazin | 25879 | BCA in Cyber Security, Ethical Hacking & Digital Foreignsic | VI | Week 1 | 2026-03-23 | 2026-03-24 | Completed | Requirements mapped.
SC-02 | System Architecture & High-Level Design (HLD) creation | Design and Development of Identity Security Framework for Supply Chain | Mohammed Nazin | 25879 | BCA in Cyber Security, Ethical Hacking & Digital Foreignsic | VI | Week 1 | 2026-03-25 | 2026-03-26 | Completed | Infrastructure design approved.
SC-03 | Environment setup, dependencies, and git initialization | Design and Development of Identity Security Framework for Supply Chain | Mohammed Nazin | 25879 | BCA in Cyber Security, Ethical Hacking & Digital Foreignsic | VI | Week 1 | 2026-03-27 | 2026-03-28 | Completed | Virtual environment ready.
SC-04 | Database Modeling (User hierarchies, Cargo tracking schemas) | Design and Development of Identity Security Framework for Supply Chain | Mohammed Nazin | 25879 | BCA in Cyber Security, Ethical Hacking & Digital Foreignsic | VI | Week 2 | 2026-03-30 | 2026-03-31 | Completed | Cargo models established.
SC-05 | Implementing Core User Authentication & Google SSO | Design and Development of Identity Security Framework for Supply Chain | Mohammed Nazin | 25879 | BCA in Cyber Security, Ethical Hacking & Digital Foreignsic | VI | Week 2 | 2026-04-01 | 2026-04-03 | Completed | SSO functional.
SC-06 | Integrating TOTP-based Multi-Factor Authentication (MFA) | Design and Development of Identity Security Framework for Supply Chain | Mohammed Nazin | 25879 | BCA in Cyber Security, Ethical Hacking & Digital Foreignsic | VI | Week 3 | 2026-04-06 | 2026-04-07 | Completed | 2FA fully enforced.
SC-07 | RBAC Integration (Supplier, Manager, Logistics routing access) | Design and Development of Identity Security Framework for Supply Chain | Mohammed Nazin | 25879 | BCA in Cyber Security, Ethical Hacking & Digital Foreignsic | VI | Week 3 | 2026-04-08 | 2026-04-09 | Completed | Role mapping via OAuth successful.
SC-08 | Field-Level Encryption for Cargo Manifests (Origin/Dest/Content) | Design and Development of Identity Security Framework for Supply Chain | Mohammed Nazin | 25879 | BCA in Cyber Security, Ethical Hacking & Digital Foreignsic | VI | Week 3 | 2026-04-10 | 2026-04-11 | Completed | Shield module applied successfully.
SC-09 | Developing Supplier Dashboard (Dispatch APIs, creation forms) | Design and Development of Identity Security Framework for Supply Chain | Mohammed Nazin | 25879 | BCA in Cyber Security, Ethical Hacking & Digital Foreignsic | VI | Week 4 | 2026-04-13 | 2026-04-14 | Completed | Suppliers can dispatch items.
SC-10 | Developing Manager Dashboard (Authorization and override logic) | Design and Development of Identity Security Framework for Supply Chain | Mohammed Nazin | 25879 | BCA in Cyber Security, Ethical Hacking & Digital Foreignsic | VI | Week 4 | 2026-04-15 | 2026-04-16 | Completed | Admin approvals functional.
SC-11 | Logistics Dashboard & Geo-Telemetry Implementation (Map rendering) | Design and Development of Identity Security Framework for Supply Chain | Mohammed Nazin | 25879 | BCA in Cyber Security, Ethical Hacking & Digital Foreignsic | VI | Week 4 | 2026-04-17 | 2026-04-18 | Completed | Fleet tracking visualized.
SC-12 | App Hardening (Limiter, Security Headers, CSRF protection) | Design and Development of Identity Security Framework for Supply Chain | Mohammed Nazin | 25879 | BCA in Cyber Security, Ethical Hacking & Digital Foreignsic | VI | Week 5 | 2026-04-20 | 2026-04-21 | Completed | Anti-hack measures deployed.
SC-13 | End-to-End System Testing & Bug Fixing | Design and Development of Identity Security Framework for Supply Chain | Mohammed Nazin | 25879 | BCA in Cyber Security, Ethical Hacking & Digital Foreignsic | VI | Week 5 | 2026-04-22 | 2026-04-23 | Completed | Performance optimized.
SC-14 | Final Report Generation, LLD, and Source Code Packaging | Design and Development of Identity Security Framework for Supply Chain | Mohammed Nazin | 25879 | BCA in Cyber Security, Ethical Hacking & Digital Foreignsic | VI | Week 5 | 2026-04-24 | 2026-04-25 | Completed | Delivery artifacts complete.